## Munka1
Tasks | Details | Responsible | Participants | Start date | End date | Goal | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
Kick-off meeting | Kick-off between the master and the customer | Attila Farkas (Scrum master) | Customer, Scrum master | 2023-11-16 | 2023-11-16 | Interpretation of customer requirements
Delegate the tasks to the team members | Assign team roles and responsibilities | Attila Farkas (Scrum master) | Attila Farkas, András Kerecsendi, Alex Apjok, Szilveszter Csordás, László Póta | 2023-11-17 | 2023-11-17 | Assign tasks to team members, Create the project timeline/workflow
Create team workspace | Set up collaboration tools and communication channels | Attila Farkas (Scrum master) | All team members | 2023-11-17 | 2023-11-17 | Establish a space for communication and document sharing
Project workflow | Define the workflow and tools of development | András Kerecsendi (Lead dev.) | All team members | 2023-11-17 | 2023-11-17 | To make a clear workflow for milestones, sub-projects, and code deployment
Features to develop - Milestones | Set project milestones to track progress and achievements | Attila Farkas (Scrum master) | Attila Farkas | 2023-11-18 | 2023-11-18 | Set project milestones to track progress and achievements
Develop | Develop |  |  | 2023-11-17 | 2023-11-22
Project review meeting - Milestone | Review and reflect on the progress. Make adjustments as needed | Attila Farkas (Scrum master) | All team members | 2023-11-22 | 2023-11-22 | Share individual achievements, Discuss challenges and concerns if there is any
Project status meeting | Communicate the current status and providing an overview. Addressing any questions or concerns | Attila Farkas (Scrum master) | Customer, Scrum master | 2023-11-23 | 2023-11-23 | Maintain transparency, Ensure the customer that the final deliverables will meet his requirements
Features to develop - Pull requests and code reviews | Implement a system for code review and collaboration | Alex Apjok (Senior dev.) | Alex Apjok | 2023-11-24 | 2023-11-25 | Implement a system for code review and collaboration
Approval workflows | Establish a process for approval before merging code changes | András Kerecsendi (Lead dev.) | András Kerecsendi | 2023-11-25 | 2023-11-26 | Establish a process for approval before merging code changes
Releases (tags) Milestone | Plan and execute version releases | András Kerecsendi (Lead dev.) | András Kerecsendi | 2023-11-26 | 2023-11-27 | Plan and execute version releases
Release notes | Document release notes for each version to communicate changes | Alex Apjok (Senior dev.) | Alex Apjok | 2023-11-27 | 2023-11-28 | Document release notes for each version to communicate changes
Documentation | Create a comprehensive documentation for the project which can be used during the coaching | László Póta (Junior dev.) | László Póta | 2023-11-28 | 2023-12-01 | Create a comprehensive documentation for the project which can be used during the coaching
Coaching of colleagues - Milestone | Coaching of the colleagues who will use the end-product | László Póta (Junior dev.) | László Póta, Customer colleagues | 2023-12-01 | 2023-12-01 | Make sure that the usage of the product is clear for the customer, Show the capabilities of the software
Handover - Milestone | Delivery of the end-product | Attila Farkas (Scrum master) | Customer, Scrum master | 2023-12-02 | 2023-12-02 | Smooth and successful transition of the project, Maintain a positive relationship with the customer for future collaborations
Retrospective | Review the project | Attila Farkas (Scrum master) | All team members | 2023-12-03 | 2023-12-03 | Review the outcomes, Reflect on the work, Discuss consequences

## Munka2
| Tasks | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
1 | Kick-off meeting
2 | Delegate the tasks to the team members
3 | Create team workspace
4 | Project workflow
5 | Features to develop - Milestones
6 | Develop
7 | Project review meeting - Milestone
8 | Project status meeting
9 | Features to develop - Pull requests and code reviews
10 | Approval workflows
11 | Releases (tags) Milestone
12 | Release notes
13 | Documentation
14 | Coaching of colleagues - Milestone
15 | Handover - Milestone
16 | Retrospective
|  |  |  | Start |  |  | Milestone |  |  | Finish